## Sprint Backlog Report
Definitions, Acronyms and Abbreviations
No. | Term | Definitions or Description
1 | UI | User Interface

## Sprint 1
Project Name | University Reviews
Module Name | Sprint 1
Development Team | C1SE04
Start Date | 2020-08-29
End Date | 2020-09-25
Sprint 1 Report
| No. | Member Name | Estimate | Actual | [14 empty] | Kết thúc nhiệm vụ
| 1 | Toi Nguyen Van Minh | 65 | 66
| 2 | Thien Nguyen Huu | 47 | 49 | [14 empty] | Trễ
| 3 | Thuong Huynh Thi Quy | 42 | 42
| 4 | Sang Ho Xuan | 52 | 55 | [14 empty] | Trước thời hạn
| Total |  | 206 | 212
Estimate
Sprint 1 | Component | Task Name | Responsible Member | Estimate | Total | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25
| Start Up | Sprint Plan Meeting | Team | 12 | 12 | 4 | 0
|  | Create Sprint Backlog | Thuong | 10 | 10 | 8 | 3 | 0
|  | Create Test Plan | Thuong | 4 | 4 | 4 | 2 | 0
|  | Architecture Design | Toi, Thuong | 10 | 10 | 8 | 6 | 4 | 0
| Design UI | Design UI of “Login” | Thien | 4 | 4 | 0
|  | Design UI of “Page not found” | Thuong | 3 | 3 | 0
|  | Design UI of “Register” | Thien | 3 | 3 | 0
|  | Design UI of “Not found” | Thuong | 3 | 3 | 3 | 0
|  | Design UI of “Homepage” | Thien | 4 | 4 | 4 | 0
|  | Design UI of “Information about the university” | Sang | 4 | 4 | 2 | 0
| Design Test Case | Design Test case of “Login” | Sang | 2 | 2 | 2 | 2 | 0
|  | Design Test case of “Page not found” | Thien | 2 | 2 | 2 | 2 | 0
|  | Design Test case of “Register” | Sang | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case of “Not found” | Sang | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case of “Homepage” | Sang, Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Design Test case of “Information about the university” | Sang, Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Coding | Set up front-end develop environment | Sang | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 0
|  | Set up back-end develop environment | Toi | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | Code "Login" back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code UI "Login" | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code "Register" back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI "Register" | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI "Not found" | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code "Homepage" back-end | Toi | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
|  | Code UI "Homepage" | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI "Information about the university" | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code "Information about the university" back-end | Toi | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 0
| Testing | Test feature “Login” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Register” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Homepage” | Thien | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Information about the university” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Fixing Bugs | Fix bug Sprint 1 | Toi, Thien, Sang | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 25 | 15 | 0
| Re-Testing | Re-test Sprint 1 | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Release Sprint 1 | Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 4 | 0
|  |  | Total | 206 | 206 | 181 | 159 | 148 | 140 | 140 | 132 | 126 | 124 | 120 | 116 | 102 | 102 | 96 | 90 | 79 | 70 | 67 | 67 | 65 | 59 | 59 | 45 | 35 | 20 | 10 | 4 | 0 | 0
Actual
Sprint 1 | Component | Task Name | Responsible Member | Actual | Total | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25
| Start Up | Sprint Plan Meeting | Team | 12 | 12 | 4 | 3
|  | Create Sprint Backlog | Thuong | 10 | 10 | 8 | 3 | 0
|  | Create Test Plan | Thuong | 4 | 4 | 4 | 2 | -1
|  | Architecture Design | Toi, Thuong | 10 | 10 | 8 | 6 | 4 | 0
| Design UI | Design UI of “Login” | Thien | 4 | 4 | 0
|  | Design UI of “Page not found” | Thuong | 3 | 3 | 0
|  | Design UI of “Register” | Thien | 3 | 3 | -1
|  | Design UI of “Coming soon” | Thuong | 3 | 3 | 3 | 0
|  | Design UI of “Homepage” | Thien | 4 | 4 | 4 | 1
|  | Design UI of “Information about the university” | Sang | 4 | 4 | 2 | 2
| Design Test Case | Design Test case of “Login” | Sang | 2 | 2 | 2 | 2 | 0
|  | Design Test case of “Page not found” | Thien | 2 | 2 | 2 | 2 | 2
|  | Design Test case of “Register” | Sang | 2 | 2 | 2 | 2 | 2 | 2
|  | Design Test case of “Coming soom” | Sang | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case of “Homepage” | Sang, Thien | 4 | 4 | 4 | 4 | 4 | 4 | 2 | -1
|  | Design Test case of “Information about the university” | Sang, Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0
| Coding | Set up front-end develop environment | Sang | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 0
|  | Set up back-end develop environment | Toi | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 2
|  | Code "Login" back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code UI "Login" | Sang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code "Register" back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1
|  | Code UI "Register" | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI "Coming soom" | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code "Homepage" back-end | Toi | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
|  | Code UI "Homepage" | Thien | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code UI "Information about the university" | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code "Information about the university" back-end | Toi | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 0
| Testing | Test feature “Login” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | -2
|  | Test feature “Register” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | -2
|  | Test feature “Homepage” | Thien | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Information about the university” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Fixing Bugs | Fix bug Sprint 1 | Toi, Thien, Sang | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 25 | 15 | 5
| Re-Testing | Re-test Sprint 1 | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
| Searching | Release Sprint 1 | Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 4 | 2
|  |  | Actual | 212 | 212 | 186 | 171 | 155 | 148 | 144 | 136 | 134 | 129 | 129 | 125 | 119 | 108 | 101 | 94 | 83 | 73 | 70 | 70 | 66 | 60 | 62 | 45 | 35 | 25 | 12 | 4 | 2 | 0
|  |  | Estimate | 206 | 206 | 181 | 159 | 148 | 140 | 140 | 132 | 126 | 124 | 120 | 116 | 110 | 102 | 96 | 90 | 79 | 70 | 67 | 67 | 65 | 59 | 59 | 45 | 35 | 20 | 10 | 4 | 0 | 0

## Sprint 2
Project Name | University Reviews
Module Name | Sprint 2
Development Team | C1SE04
Start Date | 2020-09-25
End Date | 2020-10-22
| Sprint 2 Report | [17 empty] | Kết thúc nhiệm vụ
| No. | Member Name | Estimate | Actual
| 1 | Toi Nguyen Văn Minh | 60.5 | 62.5 | [14 empty] | Trễ
| 2 | Thien Nguyen Huu | 52 | 55
| 3 | Thuong Huynh Thi Quy | 46 | 47 | [14 empty] | Trước thời hạn
| 4 | Sang Ho Xuan | 51.5 | 52.5
| Total |  | 210 | 217
Estimate
Sprint 2 | Component | Task Name | Responsible Member | Estimate | Total | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22
| Start Up | Sprint Plan Meeting | Team | 12 | 12 | 0
|  | Create Sprint Backlog | Thuong | 9 | 9 | 4 | 3 | 0
|  | Update Architecture | Toi, Thuong | 8 | 8 | 8 | 4 | 0
|  | Create Test Plan | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Update Database | Toi, Sang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Database Design Document | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design UI | Design UI “Specialized page” | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI “Cooperation page” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Gallery page” | Thuong | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Topic detail page” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Comment page” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Post topic” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Edit personal information” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Personal page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design Test case | Design Test case feature “Specialized page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case feature “Cooperation page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case feature “Gallery page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case feature “Topic detail page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case feature “Comment page” | Sang | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Design Test case feature “Post topic” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Test case feature “Edit personal information” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case feature “Personal page” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Coding | Code “Specialized page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Specialized page” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code “Cooperation page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code UI of “Cooperation page” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code “Gallery page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Gallery page” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0
|  | Code “Topic detail page” back end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Topic detail page” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Comment page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Comment page” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code " Post topic " back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Post topic” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Edit personal information" back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Edit personal information” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Personal page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of "Personal page" | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Testing | Test feature “Specialized page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Cooperation” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Test feature “Gallery page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Topic detail page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Comment page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Post topic” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Edit personal information” | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
|  | Test feature “Personal page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Fixing bugs | Fix bug “Sprint 2” | Toi, Thien, Sang | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 27 | 24 | 12 | 9 | 3 | 0
| Re-testing | Re-test “Sprint 2” | Thuong, Thien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | Release Sprint 2 | Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 4 | 0
|  |  | Total | 210 | 210 | 192 | 187 | 180 | 180 | 180 | 169 | 167 | 158 | 150 | 144 | 140 | 134 | 131 | 117 | 100 | 89 | 71 | 59 | 51 | 48 | 36 | 33 | 27 | 20 | 8 | 4
Actual
Sprint 2 | Component | Task Name | Responsible Member | Estimate | Actual | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22
| Start Up | Sprint Plan Meeting | Team | 12 | 12 | 5
|  | Create Sprint Backlog | Thuong | 9 | 9 | 4 | 3 | 0
|  | Update Architecture | Toi, Thuong | 8 | 8 | 8 | 4 | 1
|  | Create Test Plan | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Update Database | Toi, Sang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2
|  | Database Design Document | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design UI | Design UI “Specialized page” | Thien | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Design UI “Cooperation page” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Gallery page” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1
|  | Design UI of “Topic detail page” | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Comment page” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Post topic” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | -1
|  | Design UI of “Edit personal information” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Personal page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design Test Case | Design Test case feature “Specialized page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
|  | Design Test case feature “Cooperation page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
|  | Design Test case feature “Gallery page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case feature “Topic detail page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case feature “Comment page” | Sang | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | -1
|  | Design Test case feature “Post topic” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Test case feature “Edit personal information” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case feature “Personal page” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Coding | Code “Specialized page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3
|  | Code UI of “Specialized page” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code “Cooperation page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | -2
|  | Code UI of “Cooperation page” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code “Gallery page” back-end | Toi | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Code UI of “Gallery page” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0
|  | Code “Topic detail page” back end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Topic detail page” | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | -2
|  | Code “Comment page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Comment page” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code " Post topic " back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Post topic” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Edit personal information" back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Edit personal information” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Personal page” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
|  | Code UI of "Personal page" | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Testing | Test feature “Specialized page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Cooperation” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1
|  | Test feature “Gallery page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Topic detail page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | -1
|  | Test feature “Comment page” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Post topic” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1
|  | Test feature “Edit personal information” | Thien | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
|  | Test feature “Personal page” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Fixing bugs | Fix bug “Sprint 2” | Toi, Thien, Sang | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 30 | 25 | 19 | 10 | 5
| Re-testing | Re-test “Sprint 2” | Thuong, Thien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | Release Sprint 2 | Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 8 | 4 | 2
|  |  | Actual | 217 | 217 | 203 | 193 | 187 | 186 | 186 | 177 | 173 | 166 | 155 | 151 | 145 | 139 | 135 | 122 | 107 | 93 | 76 | 61 | 60 | 54 | 49 | 43 | 34 | 25 | 12 | 4 | 2 | 0
|  |  | Estimate | 210 | 210 | 192 | 187 | 180 | 180 | 180 | 169 | 167 | 158 | 150 | 144 | 140 | 134 | 131 | 117 | 100 | 89 | 71 | 59 | 51 | 48 | 36 | 33 | 27 | 20 | 8 | 4 | 0 | 0

## Sprint 3
Project Name | University Reviews
Module Name | Sprint 3
Development Team | C1SE04
Start Date | 2020-10-22
End Date | 2020-11-11 | [17 empty] | Kết thúc nhiệm vụ
| Sprint 3 Report | [17 empty] | Trễ
| No. | Member Name | Estimate | Actual
| 1 | Toi Nguyen Van Minh | 46 | 47 | [14 empty] | Trước thời hạn
| 2 | Thien Nguyen Huu | 30 | 32
| 3 | Thuong Huynh Thi Quy | 34 | 35
| 4 | Sang Ho Xuan | 31 | 33
| Total |  | 141 | 147
Estimate
Sprint 3 | Component | Task Name | Responsible Member | Estimate | Total | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11
| Start Up | Sprint Plan Meeting | Team | 12 | 12 | 0
|  | Create Sprint Backlog | Thuong | 8 | 8 | 6 | 2 | 0
|  | Create Test Plan | Thuong | 4 | 4 | 4 | 4 | 0
|  | Update Architecture | Toi, Thuong | 8 | 8 | 8 | 4 | 0
|  | Update Database | Toi, Sang | 4 | 4 | 4 | 4 | 4 | 0
|  | Database Design Document | Toi | 4 | 4 | 4 | 4 | 4 | 0
| Design UI | Design UI of “Login of university” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of "Login of admin" | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Main page university” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Edit information” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design Test case | Design Test case of “Login of university” | Thien | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Design Test case of “Login of admin” | Thuong | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Design Test case of “Main page university” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case of “Edit information” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Coding | Code “Login of university” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Login of university” | Sang | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code “Login of admin” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Login of admin” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Main page university” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code UI of “Main page university” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code “Edit information ” back-end | Toi | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
|  | Code UI of “Edit information” | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Testing | Test feature “Login of university” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
|  | Test feature “Login of admin” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Main page university” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Test feature “Edit information” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Fixing bugs | Fix bug “Sprint 3” | Toi, Thien, Sang | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 9 | 6 | 0
| Re-testing | Re-test “Sprint 3” | Team | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Release Sprint 3 | Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 4 | 0
|  |  | Total | 141 | 141 | 127 | 119 | 109 | 101 | 101 | 97 | 94 | 91 | 87 | 83 | 74 | 70 | 64 | 58 | 50 | 45 | 33 | 30 | 16 | 4 | 0
Actual
Sprint 3 | Component | Task Name | Responsible Member | Estimate | Actual | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12
| Start Up | Sprint Plan Meeting | Team | 12 | 12 | 0
|  | Create Sprint Backlog | Thuong | 8 | 8 | 6 | 2 | 2
|  | Create Test Plan | Thuong | 4 | 4 | 4 | 4 | 2
|  | Update Architecture | Toi, Thuong | 8 | 8 | 8 | 4 | -1
|  | Update Database | Toi, Sang | 4 | 4 | 4 | 4 | 4 | 1
|  | Database Design Document | Toi | 4 | 4 | 4 | 4 | 4 | 0
| Design UI | Design UI of “Login of university” | Sang | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2
|  | Design UI of "Login of admin" | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Main page university” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Edit information” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
| Design Test case | Design Test case of “Login of university” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test case of “Login of admin” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | -1
|  | Design Test case of “Main page university” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
|  | Design Test case of “Edit information” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Coding | Code “Login of university” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
|  | Code UI of “Login of university” | Sang | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code “Login of admin” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | -2
|  | Code UI of “Login of admin” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Main page university” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code UI of “Main page university” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1
|  | Code “Edit information ” back-end | Toi | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2
|  | Code UI of “Edit information” | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Testing | Test feature “Login of university” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1
|  | Test feature “Login of admin” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “Main page university” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Test feature “Edit information” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Fixing bugs | Fix bug “Sprint 3” | Toi, Thien, Sang | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 15 | 9 | 6 | 3
| Re-testing | Re-test “Sprint 3” | Team | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0
|  | Release Sprint 3 | Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 8 | 4 | 0
|  |  | Actual | 147 | 147 | 133 | 125 | 118 | 108 | 107 | 104 | 98 | 94 | 91 | 88 | 75 | 73 | 68 | 61 | 56 | 39 | 33 | 28 | 17 | 8 | 4 | 0
|  |  | Estimate | 141 | 141 | 127 | 119 | 109 | 101 | 101 | 97 | 94 | 91 | 87 | 83 | 74 | 70 | 64 | 58 | 50 | 45 | 33 | 30 | 16 | 4 | 0 | 0

## Sprint 4
Project Name | University Reviews
Module Name | Sprint 4
Development Team | C1SE04
Start Date | 2020-11-11
End Date | 2020-12-01
Sprint 4 Report
| No. | Member Name | Estimate | Actual
| 1 | Toi Nguyen Van Minh | 44 | 45
| 2 | Thien Nguyen Huu | 49 | 50 | [14 empty] | Kết thúc nhiệm vụ
| 3 | Thuong Huynh Thi Quy | 40 | 42
| 4 | Sang Ho Xuan | 42 | 43 | [14 empty] | Trễ
| Total |  | 175 | 180
Trước thời hạn
Estimate
Sprint 4 | Component | Task Name | Responsible Member | Estimate | Total | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01
| Start Up | Sprint Plan Meeting | Team | 12 | 12 | 0
|  | Sprint Backlog | Thuong | 4 | 4 | 0
|  | Database Design | Sang | 4 | 4 | 4 | 0
| Design UI | Design UI of “ Manage Account” | Thuong | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Manage Comment” | Thuong | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Manage Galaries” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Manage partners” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Manage topic” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of "Creat account" | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design Test Case | Design Test Case of “ Manage Account” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case of “Manage Comment” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case of “Manage Galaries” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case of “Manage partners” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case of “Manage topic” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case of “Creat account” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Coding | Code UI of “Manage Account ” Frontend | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
|  | Code “Manage Account” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Manage Comment” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Manage Comment” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code UI of “Manage Galaries” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code “Manage Galaries” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Manage partners” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code “Manage parters” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Manage topic” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code “Manage topic” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of "Creat account" | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code "Creat account" back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Testing | Test feature “Manage Account” | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Test feature “Manage Comment” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Test feature “Manage Galaries” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Test feature “Manage partners” | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Test feature “Manage topic” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2
|  | Test feature "Creat account" | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Fixing bugs | Fix bugs “Sprint 4” | Toi, Thien, Sang | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 15 | 0
| Re-testing | Re-test integration | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Re-fixing | Re-fix integration "Sprint 4" | Team | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 6 | 0
|  | Release Sprint 4 | Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 9 | 6 | 3 | 0
|  |  | Total | 175 | 175 | 159 | 155 | 155 | 149 | 143 | 137 | 131 | 129 | 129 | 128 | 126 | 120 | 110 | 100 | 96 | 84 | 70 | 39 | 16 | 3 | 0
Actual
#REF! | Component | Task Name | Responsible Member | Estimate | Actual | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02
| Start Up | Sprint Plan Meeting | Team | 12 | 12 | 4
|  | Sprint Backlog | Thuong | 4 | 4 | 0
|  | Database Design | Sang | 4 | 4 | 4 | 0
| Design UI | Design UI of “ Manage Account” | Thuong | 3 | 3 | 3 | 3 | 3 | 1
|  | Design UI of “Manage Comment” | Thuong | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Manage Galaries” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Manage partners” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 1
|  | Design UI of “Manage topic” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of "Creat account" | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design Test Case | Design Test Case of “ Manage Account” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | -1
|  | Design Test Case of “Manage Comment” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case of “Manage Galaries” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case of “Manage partners” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case of “Manage topic” | Sang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Design Test Case of “Creat account” | Thuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Coding | Code UI of “Manage Account ” | Thien | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | -1
|  | Code “Manage Account” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
|  | Code UI of “Manage Comment” | Thien | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code “Manage Comment” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code UI of “Manage Galaries” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
|  | Code “Manage Galaries” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1
|  | Code UI of “Manage partners” | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code “Manage parters” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Manage topic” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1
|  | Code “Manage topic” back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of "Creat account" | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | -2
|  | Code "Creat account" back-end | Toi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Testing | Test feature “Manage Account” | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
|  | Test feature “Manage Comment” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Test feature “Manage Galaries” | Thien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Test feature “Manage partners” | Thuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | -1
|  | Test feature “Manage topic” | Thuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1
|  | Test feature "Creat account" | Sang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Fixing bugs | Fix bugs “Sprint 4” | Toi, Thien, Sang | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 16 | 0
| Re-testing | Re-test integration | Thuong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2
| Re-fixing | Re-fix integration "Sprint 4" | Team | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 6 | 0
|  | Release Sprint 4 | Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 9 | 6 | 3 | 3
|  |  | Actual | 180 | 180 | 168 | 160 | 160 | 155 | 149 | 141 | 138 | 134 | 134 | 133 | 130 | 127 | 118 | 105 | 99 | 90 | 77 | 38 | 17 | 5 | 3 | 0
|  |  | Estimate | 175 | 175 | 159 | 155 | 155 | 149 | 143 | 137 | 131 | 129 | 129 | 128 | 126 | 120 | 110 | 100 | 96 | 84 | 70 | 39 | 16 | 3 | 0